## Sheet1
Project Schedule |  | March |  |  |  | April |  |  |  | May |  |  |  | Completed
| Week (#) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | In Progress
Programming Project 1 | Start date | 2017-03-02 | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 10//4 | 2017-03-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | Planned
| End date | 2017-03-06 | 2017-03-13 | 2017-03-20 | 2017-03-27 | 2017-04-03 | 2017-04-10 | 2017-03-24 | 2017-05-01 | 2017-05-08 | 2017-05-15 | 2017-05-22 | 2017-05-29 | Overdue
Activity | Progress
Preparation and Planning
Develope project planning | 100%
Approve project proposal | 100%
Setup AWS server | 100%
Prepare prototype | 100%
Setup github | 100%
Create user stories | 100%
Server setup | 100%
Development
Develop website prototype | 100%
setup API | 100%
UI website design | 100%
layout for register and login | 100%
register and login functionality | 100%
seller functionality | 100%
buyer functionality | 100%
post functionality | 100%
edit and delete functionality | 100%
100%
100%
Test & Debugging
Login test | 100%
Register test | 100%
Input data test | 100%
Buyer test | 100%
Seller test | 100%
Input data test | 100%
Database test | 100%
Debugging
Documentation
Project charter | 100%
Setup guide | 100%
Risk register | 100%
Project schedule/gantt chart | 100%
Tools research | 100%
Tools report | 100%
Peer Review | 100%
Meeting minutes | 100%
Timesheet | 100%
project report | 100%