## Sheet1
Project 1 - Buyer/Seller matchmaking website
Timesheet report
Week | Task | Assign to | start | end | hours
1 | setup server on AWS | Jiajun He | 2017-03-01 | 2017-03-08 | 2
| Develop project scope | Jason Le | 2017-03-01 | 2017-03-08 | 2
| Prepare general requirement | Pavitra Vathsalaraj | 2017-03-01 | 2017-03-08 | 2
| Create Meeting minute | Pavitra Vathsalaraj | 2017-03-01 | 2017-03-08 | 0.5
| Setup Trello | Saelon Kim | 2017-03-01 | 2017-03-08 | 0.5
2 | User stories | Jiajun He | 2017-03-08 | 2017-03-15 | 2
| Brainstorm website features and functions | Jason Le | 2017-03-08 | 2017-03-15 | 2
| Discuss website features & framework to use | Pavitra Vathsalaraj | 2017-03-08 | 2017-03-15 | 2
| Create Meeting minute | Pavitra Vathsalaraj | 2017-03-08 | 2017-03-15 | 0.5
| Search php frameworks & select Laravel | Saelon Kim | 2017-03-08 | 2017-03-15 | 1
3 | Product backlog | Jiajun He | 2017-03-15 | 2017-03-22 | 1
| Project Charter(Summary and scope) | Jiajun He | 2017-03-15 | 2017-03-22 | 2
| Website prototype | Jiajun He | 2017-03-15 | 2017-03-22 | 4
| Laravel installation guide | Jiajun He | 2017-03-15 | 2017-03-22 | 1.5
| WBS | Jason Le | 2017-03-15 | 2017-03-22 | 2
| Project Charter | Jason Le | 2017-03-15 | 2017-03-22 | 2
| Research search methods | Jason Le | 2017-03-15 | 2017-03-22 | 2
| Website design | Pavitra Vathsalaraj | 2017-03-15 | 2017-03-22 | 1
| Project charter | Pavitra Vathsalaraj | 2017-03-15 | 2017-03-22 | 1
| Create Meeting minute | Pavitra Vathsalaraj | 2017-03-15 | 2017-03-22 | 0.5
| Install Laravel into AWS server | Saelon Kim | 2017-03-15 | 2017-03-22 | 3
| Make a list of small functions to be in the website | Saelon Kim | 2017-03-15 | 2017-03-22 | 1
4 | Implementation of register & login function | Jiajun He | 2017-03-22 | 2017-03-29 | 10
| Layout for register & login | Jiajun He | 2017-03-22 | 2017-03-29 | 5
| Prototype change | Jiajun He | 2017-03-22 | 2017-03-29 | 0.25
| Change user stories | Jiajun He | 2017-03-22 | 2017-03-29 | 0.5
| Set up Github | Jiajun He | 2017-03-22 | 2017-03-29 | 1.5
| Research and learn laravel | Jason Le | 2017-03-22 | 2017-03-29 | 3
| Setup Github | Jason Le | 2017-03-22 | 2017-03-29 | 0.5
| Minor Testing | Jason Le | 2017-03-22 | 2017-03-29 | 0.5
| Layout for register & login | Pavitra Vathsalaraj | 2017-03-22 | 2017-03-29 | 3
| Install laravel | Pavitra Vathsalaraj | 2017-03-22 | 2017-03-29 | 2
| Setup github | Pavitra Vathsalaraj | 2017-03-22 | 2017-03-29 | 0.5
| Create Meeting minute | Pavitra Vathsalaraj | 2017-03-22 | 2017-03-29 | 0.5
| Research and learn laravel | Saelon Kim | 2017-03-22 | 2017-03-29 | 3
| Layout for register & login | Saelon Kim | 2017-03-22 | 2017-03-29 | 2
| Finish install & setting up Laravel | Saelon Kim | 2017-03-22 | 2017-03-29 | 3
5 | Publish post function | Jiajun He | 2017-03-29 | 2017-04-05 | 5
| Layout for "create post" | Jiajun He | 2017-03-29 | 2017-04-05 | 2
| Change password format | Jiajun He | 2017-03-29 | 2017-04-05 | 0.3
| Update server website | Jiajun He | 2017-03-29 | 2017-04-05 | 2
| Implement Search function | Jason Le | 2017-03-29 | 2017-04-05 | 4
| Create change password page | Pavitra Vathsalaraj | 2017-03-29 | 2017-04-05 | 2
| Create edit profile page | Pavitra Vathsalaraj | 2017-03-29 | 2017-04-05 | 1
| Create my account page | Pavitra Vathsalaraj | 2017-03-29 | 2017-04-05 | 1
| Research and learn laravel | Pavitra Vathsalaraj | 2017-03-29 | 2017-04-05 | 4
| Create Meeting minute | Pavitra Vathsalaraj | 2017-03-29 | 2017-04-05 | 0.5
| Create Add description | Saelon Kim | 2017-03-29 | 2017-04-05 | 1.5
| Create Edit description pages | Saelon Kim | 2017-03-29 | 2017-04-05 | 1.5
6-7 | Implement "User interest" model | Jiajun He | 2017-05-04 | 2017-04-12 | 6
| Put user interest onto relevent page | Jiajun He | 2017-05-04 | 2017-04-12 | 0.5
| Change model structure:Posts, buyer & seller | Jiajun He | 2017-05-04 | 2017-04-12 | 3
| Change "create post" | Jiajun He | 2017-05-04 | 2017-04-12 | 2
| Update server website | Jiajun He | 2017-05-04 | 2017-04-12 | 3
| Testing | Jason Le | 2017-05-04 | 2017-04-12 | 3
| Change to search function | Jason Le | 2017-05-04 | 2017-04-12 | 1.5
| Update Register layout | Saelon Kim | 2017-05-04 | 2017-04-12 | 1
| Update Create post layout (buyer/seller) | Saelon Kim | 2017-05-04 | 2017-04-12 | 1
| Create post layout for buyer/seller | Pavitra Vathsalaraj | 2017-05-04 | 2017-04-12 | 1
| Learn more laravel functionalities | Pavitra Vathsalaraj | 2017-05-04 | 2017-04-12 | 4
| Create Meeting minute | Pavitra Vathsalaraj | 2017-05-04 | 2017-04-12 | 0.5
8-9 | Finalise "delete" function | Jiajun He | 2017-12-04 | 2017-04-19 | 0.5
| Change User preference model | Jiajun He | 2017-12-04 | 2017-04-19 | 3
| Finalise "delete post" function | Jiajun He | 2017-12-04 | 2017-04-19 | 1
| View account/ View description detail/ Display posts | Jiajun He | 2017-12-04 | 2017-04-19 | 6
| Human Validation for viewing contact details | Jiajun He | 2017-12-04 | 2017-04-19 | 3
| Debugging | Jiajun He | 2017-12-04 | 2017-04-19 | 2
| Update server website | Jiajun He | 2017-12-04 | 2017-04-19 | 2.5
| Testing | Jason Le | 2017-12-04 | 2017-04-19 | 4
| Research and reimplementation of Index searching | Jason Le | 2017-12-04 | 2017-04-19 | 6
| Add functions for Account detail | Saelon Kim | 2017-12-04 | 2017-04-19 | 2
| Add functions for Edit profile | Saelon Kim | 2017-12-04 | 2017-04-19 | 2
| Add functions for Change password | Saelon Kim | 2017-12-04 | 2017-04-19 | 2
| Add functions for Edit description | Saelon Kim | 2017-12-04 | 2017-04-19 | 2
| Delete account function | Pavitra Vathsalaraj | 2017-12-04 | 2017-04-19 | 2
| Create Meeting minute | Pavitra Vathsalaraj | 2017-12-04 | 2017-04-19 | 0.5
10 | Admin function | Jiajun He | 2017-04-19 | 2017-04-26 | 5
| Layout for admin pages | Jiajun He | 2017-04-19 | 2017-04-26 | 3.5
| Debugging | Jiajun He | 2017-04-19 | 2017-04-26 | 2
| Update server website | Jiajun He | 2017-04-19 | 2017-04-26 | 1
| Testing and Bug reports | Jason Le | 2017-04-19 | 2017-04-26 | 4
| Testing and Bug reports | Saelon Kim | 2017-04-19 | 2017-04-26 | 1
| Testing and Bug reports | Pavitra Vathsalaraj | 2017-04-19 | 2017-04-26 | 1
| Create Meeting minute | Pavitra Vathsalaraj | 2017-04-19 | 2017-04-26 | 0.5
11 | Debugging | Jiajun He | 2017-04-26 | 2017-05-03 | 4
| Documentation(#4,#9,#10,#12, #15) | Jiajun He | 2017-04-26 | 2017-05-03 | 6
| Update server website | Jiajun He | 2017-04-26 | 2017-05-03 | 2
| Documentation | Jason Le | 2017-04-26 | 2017-05-03 | 8
| Testing | Jason Le | 2017-04-26 | 2017-05-03 | 3
| Minor Debugging | Jason Le | 2017-04-26 | 2017-05-03 | 1
| Documentation | Saelon Kim | 2017-04-26 | 2017-05-03 | 3
| Testing | Saelon Kim | 2017-04-26 | 2017-05-03 | 0.5
| Creat project schedule/gantt chart | Pavitra Vathsalaraj | 2017-04-26 | 2017-05-03 | 3
| Documentation | Pavitra Vathsalaraj | 2017-04-26 | 2017-05-03 | 4
| Create Meeting minute |  |  |  | 0.5
Total time spent
Team
|  |  |  | Jiajun He | 95.05
|  |  |  | Jason Le | 48.5
|  |  |  | Saelon Kim | 31 hrs
|  |  |  | Pavitra Vathsalaraj | 39